Meeting Minutes

Internal Workshop – CPE Evaluators
Date: 28 April 2025
Time: 15:30–19:00 (Dhaka Time)
Venue: Google Meet

1. Participants

- Silvia Salinas Mulder (Team Leader, CPE)

- Wahidul Islam (SRHR Expert)

- Syed Shahadat Hossain (Population Dynamics Expert)

- Sanzida Akhter (Adolescents & Youth Expert)

- Sadika Akhter (Gender Equality Expert)

- Rafi Jahin (Young & Emerging Evaluator)

2. Purpose of Meeting

- Clarify roles, responsibilities, and expectations for the inception phase.

- Review the Terms of Reference (ToRs) for the evaluation team.

- Align understanding of evaluation scope, deliverables, methodology, and timeline.

- Discuss practical and logistical considerations for fieldwork planning.

- Discussion on artificial intelligence usage in the evaluation.

3. Key Discussions

3.1 ToR and Evaluation Purpose

- Independent assessment of UNFPA Bangladesh’s 10th Country Programme (2022–2026).

- Support evidence-based programming for the next cycle and knowledge-sharing objectives.

- Emphasis on cross-cutting themes: innovation, disability inclusion, leave no one behind (LNOB), and human development nexus.

- Focus on building a trust-based evaluation process that empowers national stakeholders.

3.2 Scope of Evaluation

- Timeframe: 2022 to early 2025.

- Geographic: 10 Integrated Districts, 12 Donor-specific Districts, Cox’s Bazar.

- Thematic Areas: SRHR, Adolescents & Youth, Gender Equality, Population Dynamics.

- Cross-Cutting Themes: Innovation, Disability Inclusion, LNOB, Humanitarian-Development-Peace Nexus.

3.3 Evaluation Criteria and Questions

- Relevance, Coherence, Effectiveness, Efficiency, Sustainability, Humanitarian-specific criteria (Coverage, Connectedness).

- Discussion around strengthening questions regarding crosscutting issues and adaptive management.

- Importance of critically assessing both successful and less successful interventions.

3.4 Theories of Change (ToC)

- Thematic units presented their ToCs.

- Concerns raised:

  - ToCs appear fragmented; no unified Program-wide ToC yet presented.

  - Assumptions were inconsistently interpreted—often mixed up between "risks" and "hypotheses."

  - Need for a collective discussion with CO leadership to clarify overall Theory of Change and its use during implementation.

3.5 Fieldwork Planning

- Agreement that field visits must be strategically selected, not exhaustive.

- Risk factors identified:

  - Eid-ul-Adha holidays (early June) impacting availability until June 28.

  - Monsoon season/flood risks during June–July.

  - Travel constraints inside Bangladesh (time-consuming and difficult).

- Proposal to begin Dhaka-based activities (desk reviews, stakeholder interviews) from mid-June before field deployments.

- Importance of jointly visiting certain sites to address crosscutting themes but also specialized thematic visits individually.

3.6 Quantitative Data and Surveys

- Discussed the possibility of including a small quantitative survey alongside qualitative fieldwork.

- Recognized the need for triangulation through survey, FGD, KIIs.

- Baseline and existing monitoring data sources (e.g., Violence Against Women Survey, Census Data) must be utilized to avoid creating heavy new data demands.

3.7 Timeline Adjustments

- Fieldwork now tentatively starts after Eid

- Design Phase extended in May–June for thorough preparation, risk assessment, and intervention mapping.

- Design Report first draft may need to be adjusted beyond May 6 due to missing intervention lists and stakeholder mapping.

3.8 Risk Mitigation Plan

- Need to discuss flexibility in field visits (weather, strikes, floods).

- Risk mitigation strategies (including for evaluator safety) must be integrated into fieldwork planning.

3.9 AI integration

- Rafi Jahin shared a presentation on AI related guidelines of UNFPA.

4. Immediate Next Steps

- Fieldwork starts post-Eid (tentative June 17–28 window), exact start date depends on readiness.

- Bilateral meetings to be conducted with thematic leads by this May 7-8.

- Strict human oversight over any AI-supported analysis outputs.

- Collaboration protocols: WhatsApp group created; weekly meeting on Monday is fixed.

- UNFPA Email IDs to be arranged for full access to secure resources and gemini advanced.

5. Action Points and Responsibilities

| Action Point | Responsible Person(s) |
| --- | --- |
| Create risk tracking Google Doc for field visit issues | Rafi Jahin (Link) |
| Coordinate and schedule bilateral meetings with thematic leads | Rafi Jahin |
| Arrange a field planning workshop | Rafi Jahin with the help of UNFPA team |
| Share the outline for the inception report and revised timeline for Inception Phase | Silvia Salinas Mulder |
| Document risks and recommendations collectively | All Evaluators (Link) |
| Review Handbook individually | All Evaluators |
| Arrange UNFPA Email IDs | Rafi Jahin |
| Finalize thematic area priorities for site visits | All Thematic Experts |
| Summarize phase documents | Rafi Jahin (A draft template will be share by Silvia) |
| Comparative analysis of previous reports | Rafi Jahin |
| Develop AI prompt templates for document review in all thematic areas | Rafi Jahin and all evaluators |
| Share preferences for Inception Report roles | All Evaluators |
| Share meeting notes and last recording | Rafi Jahin |